## Sheet1
Project Schedule - Group DiFA
No. | Progress Name | Target | PIC | Status | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday
[5 empty] | 2022-12-16 | 2022-12-17 | 2022-12-18 | 2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23
Project modelling |  |  |  |  | 2022-12-22: Rehearsal with Hacktiv8; 2022-12-23: Graduation Day
1. | Introduction | Pitching by everyone | All | Done | bar: 2022-12-16
2. | Problem Statement | Analysis issue statements | Okti, Yuni | Done | bar: 2022-12-16 to 2022-12-17
|  | Analysis profile | Okti, Yuni | Done | bar: 2022-12-16 to 2022-12-17
|  | Questionnaire for profiling | Okti, Yuni | Done | bar: 2022-12-16 to 2022-12-17
3. | Data Loading | Data Scraping | Natual, Gara, Jool, Afif | Done | bar: 2022-12-16 to 2022-12-17
|  | Data Cleaning | Natual, Gara, Jool, Afif | Done | bar: 2022-12-16 to 2022-12-17
4. | Exploratory Data Analysis | For presentation content | All | Done | bar: 2022-12-18
5. | Data Preprocessing* | Final data upload on github | Jool, Gara, others | Done | bar: 2022-12-18 to 2022-12-20
6. | Model Definition* | LSTM for Stocks (tested on colab) | Gara, Natual, Jool, Afif | Done | bar: 2022-12-18 to 2022-12-20
|  | Low risk model | Gara, Okti | Done | bar: 2022-12-18 to 2022-12-20
|  | Medium Risk model | Gara, Okti | Done | bar: 2022-12-18 to 2022-12-20
|  | High Risk model | Gara, Jool | Done | bar: 2022-12-18 to 2022-12-20
7. | Model Training | Same with Model Definition | Jool, Okti | Done | bar: 2022-12-18 to 2022-12-20
8. | Model Evaluation | Same with Model Definition | Jool, Okti | Done | bar: 2022-12-18 to 2022-12-20
9. | Model Saving |  | Yuni, Afif | Done | bar: 2022-12-18 to 2022-12-20
10. | Model Inference |  | Yuni, Afif | Done | bar: 2022-12-19 to 2022-12-20
11. | Backend - Frontend |  | Yuni, Afif, Natual | Done | bar: 2022-12-16 to 2022-12-21
GitHub
12. | Content | Readme writing | Okti | Done | bar: 2022-12-16 to 2022-12-21
|  | Github classroom | Natual | Done | bar: 2022-12-16
|  | Content uploaders | All | Done | bar: 2022-12-16 to 2022-12-21
Demo Program
13. | Recording | Demo Program | Afif | Done | bar: 2022-12-21
Prenstation slides
14. | Slides documentation | pptx format | All | Done | bar: 2022-12-16 to 2022-12-21
Deadline: 23:59
Additional to-do-lists:
* | Heavy works
Every progress should be uploaded on github